## Foglio1
| Year I |  |  |  | Year II
| 2026-03-01 | 2026-06-04 | 2026-09-07 | 2026-12-10 | 13-15 | 16-18 | 19-21 | 22-24
WORK PACKAGES (WP)
WP1: Simulation and Optimization
T1.1 - Requirements definition
T1.2 - SHADOW4 ray-tracing optimization
T1.3 - GEANT4 simulations
T1.4 - Final geometry selection
WP2: Instrument design and procurement
T2.1 - Mechanical design
T2.2 - Procurement of optics, mechanics and detector
T2.3 - Integration
T2.4 - Commissioning
WP3: Assembly and validation at VOXES
T3.1 - Energy calibration
T3.2 - Resolution and efficiency measurements
T3.3 - XAS/XES validation with laboratory sources
T3.4 - Readiness review
WP4: Experimental Demonstration
T4.1 - Installation at EuAPS
T4.2 - First XAS measurements
T4.3 - Feasibility demonstration
T4.4 - Final data analysis
MILESTONES (MS)
MS1. Optimized spectrometer design completed |  | x
MS2. Hardware assembled and commissioned |  |  |  | x
MS3. Laboratory validation completed | [5 empty] | x
MS4. Successful demonstration at EuAPS | [7 empty] | x