## 1_Gantt
| Year I |  |  |  | Year II
| M1-M3 | M4-M6 | M7-M9 | M10-M12 | M13-M15 | M16-M18 | M19-M21 | M22-M24
WORK PACKAGES (WP)
WP1: Simulation and Optimization | bar: Year I M1-M3 to Year I M7-M9
T1.1 - Requirements definition | bar: Year I M1-M3
T1.2 - SHADOW4 ray-tracing optimization | bar: Year I M1-M3 to Year I M4-M6
T1.3 - GEANT4 simulations | bar: Year I M4-M6 to Year I M7-M9
T1.4 - Final geometry selection | bar: Year I M7-M9
WP2: Instrument design and procurement | bar: Year I M4-M6 to Year II M13-M15
T2.1 - Mechanical design | bar: Year I M4-M6 to Year I M7-M9
T2.2 - Procurement of optics, mechanics and detector | bar: Year I M7-M9 to Year I M10-M12
T2.3 - Integration | bar: Year I M10-M12 to Year II M13-M15
T2.4 - Commissioning | bar: Year II M13-M15
WP3: Assembly and validation at VOXES | bar: Year I M10-M12 to Year II M16-M18
T3.1 - Energy calibration | bar: Year I M10-M12 to Year II M13-M15
T3.2 - Resolution and efficiency measurements | bar: Year II M13-M15 to Year II M16-M18
T3.3 - XAS/XES validation with laboratory sources | bar: Year II M13-M15 to Year II M16-M18
T3.4 - Readiness review | bar: Year II M16-M18
WP4: Experimental Demonstration | bar: Year II M16-M18 to Year II M22-M24
T4.1 - Installation at EuAPS | bar: Year II M16-M18
T4.2 - First XAS measurements | bar: Year II M16-M18 to Year II M19-M21
T4.3 - Feasibility demonstration | bar: Year II M19-M21 to Year II M22-M24
T4.4 - Final data analysis | bar: Year II M22-M24
MILESTONES (MS)
MS1. Optimized spectrometer design completed | bar: Year I M4-M6
MS2. Hardware assembled and commissioned | bar: Year I M10-M12
MS3. Laboratory validation completed | bar: Year II M16-M18
MS4. Successful demonstration at EuAPS | bar: Year II M22-M24

## 2_Gantt
WORK PACKAGE (WP) | PLANNED ACTIVITY (A) | 2027 |  |  |  | 2028
|  | 1-3 | 4-6 | 7-9 | 10-12 | 13-15 | 16-18 | 19-21 | 22-24
WP1 - Requirements, simulations and design freeze | A1.1 - Requirements definition | bar: 2027 1-3
A1.2 - SHADOW4 ray-tracing optimization | bar: 2027 1-3
A1.3 - GEANT4 fluorescence simulations | bar: 2027 4-6
A1.4 - Final geometry selection | bar: 2027 4-6
WP2 - CZT, front-end, DAQ, calibration and characterization | A2.1 - CZT detector and front-end design | bar: 2027 4-6 to 2027 7-9
A2.2 - Multichannel DAQ and signal-processing development | bar: 2027 7-9 to 2027 10-12
A2.3 - CZT calibration and performance characterization | bar: 2027 10-12 to 2028 13-15
A2.4 - Detector validation and operating-point selection | bar: 2028 13-15
WP3 - Procurement, mechanics, integration and commissioning | A3.1 - Procurement of source, optics and motion stages | bar: 2027 10-12 to 2028 13-15
A3.2 - Mechanical design and spectrometer assembly | bar: 2028 13-15 to 2028 16-18
A3.3 - Hardware, software and control-system integration | bar: 2028 13-15 to 2028 16-18
A3.4 - Instrument commissioning and verification | bar: 2028 16-18
WP4 - Ag reference samples and realistic sample demonstration | A4.1 - Ag foil calibration and reproducibility tests | bar: 2028 16-18
A4.2 - XANES validation on Ag reference compounds | bar: 2028 16-18 to 2028 19-21
A4.3 - Fluorescence XAS demonstration on a realistic sample | bar: 2028 19-21 to 2028 22-24
A4.4 - Performance map and operating-domain assessment | bar: 2028 22-24