## Slide 1: ECHO Magnet
L. Balconi
Proposal for young researchers grant – CSN5
Extremely Curved Hadrontherapy Optics Magnet

## Slide 2: About me:
2020 – Bachelor degree in Physics
  University of Milan, Medical Physics ”Feasibility study of an innovative range monitoring technique using prompt gamma in hadrontherapy”
2022 – Master degree in Fusion Plasma Physics
  University of Milan, CNR Padova – Consorzio RFX ”Set-up of the spectroscopic diagnostics for MITICA”
2022 – Present PhD in Applied Physics (Final defense expected early jan 2026)
  University of Milan, LASA laboratory ”Design and study of the IRIS 10 T Energy Saving dipole Magnet for Accelerators ESMA”
  CSC Graduate Study Fellowship Award by IEEE, Council on SuperConductivity (CSC)
PAPRICA detector
MITICA Neutral Beam Injector
ESMA dipole magnet

## Slide 3: Outline
Status of the art, Why ECHO Magnet?
Realization plan of ECHO
    Design
    Manufacturing
Timeline, risks and costs analysis
Conclusions

## Slide 4: State-of-the-art & actual R&D
Low Temperature Superconductors (LTS)
  Toshiba/NIRST: B = 2.88 T, ρ = 2.3 m,
    300 tons
  Yamagata: B = 3.5 T, ρ = 1.9 m
    200 tons
  SIG: B = 4 T, ρ = 1.65 m
  HITRI+: B = 4 T, ρ = 1.65 m
High Temperature Superconducting (HTS) tapes are promising candidates
Resistive magnets for ion gantry:
  HIT: B = 1.8 T, ρ = 3.65 m
  650 tons
m ~ 100 tons
HTS?
Notes: Dire che gli HTS sono nastri  avvolgimenti piani ok

## Slide 5: ECHO Magnet: Targets
Extremly Curved Hadrontherapy Optics (ECHO) Magnet:
Gantries and particle accelerators for hadrontherapy.
Demonstrating the Technological Readiness Level (TRL) of High Temperature Superconductors (HTS)
Energy saving with respect to classical Low Temperature Superconductors (LTS)
Modular design assembled in a curved geometry
Target central field B0 | T | 5
Curvature radius | m | 1.3
Free aperture | mm | 50
Operating temperature | K | 20
Critical current margin | N/A | >20%
Target central field B0 | T | 5
Curvature radius | m | 1.3
 | mm | 50
Operating temperature | K | 20
Critical current margin | N/A | >20%
Inner layer
Outer layer
B
B
Canted Cosine Theta - CCT
Beam-pipe
Inner layer
Outer layer
Notes: Rivisitando nota geometria CCT

## Slide 6
B = 5 T, ρ = 1.3 m
State-of-the-art & actual R&D
Low Temperature Superconductors (LTS)
  Toshiba/NIRST: B = 2.88 T, ρ = 2.3 m,
    300 tons
  Yamagata: B = 3.5 T, ρ = 1.9 m
    200 tons
  SIG: B = 4 T, ρ = 1.65 m
  HITRI+: B = 4 T, ρ = 1.65 m
High Temperature Superconducting (HTS) tapes are promising candidates
Resistive magnets for ion gantry:
  HIT: B = 1.8 T, ρ = 3.65 m
  650 tons
m ~ 100 tons

## Slide 7: ECHO Magnet: Advantages
Given the state of the art on SC dipole magnets for hadrontherapy ECHO magnet introduces:
Operation at 20 K liquid He free
  x5 energy saving factor with respect to 4.2 K (just for COP)
Modular design: industrialization and scalability
Target central field of 5 T
  20 % reduction of the curvature radius ρ
QA procedure at 77 K granted by HTS
Treatment Room
ρ
Particle Accelerator
Bending Dipoles - ECHO
Scanning Magnet

## Slide 8
Dipolar HTS magnet towards ECHO
IRIS dipole - ESMA
I.FAST CCT dipole
ECHO Magnet
Pros
Flat coils  windability
High field (10 T)
Solid design
Cons
Straight geometry
± 1.5 % field quality
Pros
Field quality
No inner junctions
Cons
Straight geometry
Complex helix-winding
Critical external junctions
Pros
Flat coils  windability
Curved geometry
Field quality
Scalability
Cons
Modules assembly on curved support
Resistive joints
Courtesy of E. De Matteis

## Slide 9: Roadmap of activities for ECHO
Phase 1
Characterization of HTS tape
Single module design and challenges
Phase 2
Electrical
Thermal and Mechanical
Mechanical Assembly
Modules manufacturing
Final Testing

## Slide 10: Roadmap of activities for ECHO
Phase 1
Characterization of HTS tape
Single module design and challenges
Phase 2
Electrical
Thermal and Mechanical
Mechanical Assembly
Modules manufacturing
Final Testing

## Slide 11: Phase 1: Characterization of HTS tape Electrical
Courtesy of C. Senatore, University of Geneva
Electrical properties are fundamental to drive the electromagnetic design of each module:
HTS tape critical current dependencies:
  Temperature
  Magnetic field
  Angular
Optimization of resistive splices
  Within each module
  Inter-module
Simple Flat
Lap
Bridge
Joint Failure
HTS tape
Insulating guide

## Slide 12: Roadmap of activities for ECHO
Phase 1
Characterization of HTS tape
Phase 2
Electrical
Thermal and Mechanical
Mechanical Assembly
Modules manufacturing
Final Testing
Single module design and challenges

## Slide 13: Phase 1: Characterization of HTS tape Thermal and Mechanical
Thermal and mechanical properties will be studied for different cables configurations:
Thermal conductivity
  Dry-wound
  Impregnated
Lower than expected Young’s modulus
  Dry-stack
  Impregnated stack

## Slide 14: Roadmap of activities for ECHO
Phase 1
Characterization of HTS tape
Phase 2
Electrical
Thermal and Mechanical
Mechanical Assembly
Modules manufacturing
Final Testing
Single module design and challenges

## Slide 15: Phase 1: Single module design
A small HTS racetrack coil design aiming at one ECHO module will be performed. The design must assess the following question:
Realize a solid design with operational margins
Achieve a repeatible field quality
Optimize resistive joints
Handle the assembly on a curved support
Set up a QA procedure in LN2
  Modularity and repeatibility of the process
Conceptual Single Module

## Slide 16: Roadmap of activities for ECHO
Phase 1
Characterization of HTS tape
Phase 2
Electrical
Thermal and Mechanical
Mechanical Assembly
Modules manufacturing
Final Testing
Single module design and challenges

## Slide 17: Phase 2: Module Manufacturing
The winding of each ECHO module will be carried out considering:
Different winding technologies using a multi-tape winding machine:
  Up to 6 tapes in parallel.
  Variable and controlled winding tension.
A classical racetrack geometry suffers from buckling:
  Alternatives/mitigations will be studied.
Winding test: single tape on plastic mandrel

## Slide 18: Roadmap of activities for ECHO
Phase 1
Characterization of HTS tape
Phase 2
Electrical
Thermal and Mechanical
Mechanical Assembly
Modules manufacturing
Final Testing
Single module design and challenges

## Slide 19: Phase 2: Mechanical assembly
The manufacturing of the ECHO module will be carried out considering:
Integrating the mechanic of each module with the curved support
Optimization of resistive junctions between modules
Possibility to exploit metallic additive manufacturing:
  Copper
  Stainless steel

## Slide 20: Roadmap of activities for ECHO
Phase 1
Characterization of HTS tape
Phase 2
Electrical
Thermal and Mechanical
Mechanical Assembly
Modules manufacturing
Final Testing
Single module design and challenges

## Slide 21: Phase 2: Final testing
8 T
SOLEMI insert
D 450 mm
h 720 mm
HiLumi
D 450 mm
h 1910 mm
Tests at 20 K will be carried out inside the IRIS variable temperature test stand for HTS magnets:
Closed loop cooling 20 K – 50 K
Based on cryocoolers and closed loop G-Helium :
  20 W @ 20 K (Adjustable T from 20 K to 50 K)
  300 W @ 55 K

## Slide 22: Project timeline
Milestones:
Deliverables:
First 10 coils
3
5
18
20
24
1
Notes: FTE x tecnici (1.4/2)
Assessment of the assembly, specificare bene del magnete finale (parte arancione della figura iniziale)
M1 (Month 6) – Completion of full 3D electromagnetic and mechanical model.
M2 (Month 10) – Successful winding and LN₂ testing of the first HTS coil module.
M3 (Month 14) – Completion of 10 coil modules with validated performance.
M4 (Month 20) – Completion of full mechanical assembly of the short MCCT prototype.
M5 (Month 24) – Completion of cryogenic testing at 20 K.
D1: Conceptual design report.
D2: Fabrication and testing logs for a HTS racetrack coil modulus, at LN₂ temperature.
D3: Assembling report of the short prototype magnet.
D4: Final test report.

## Slide 23: Risks and costs summary
About the risk analysis:
Risks are mainly calculated from the experience accumulated in the design and manufacturing of ESMA
Windability may be affected by the chosen geometry and superficial homogeneity of the tape
Protection and thermal budget must be carefully addressed, as well as field quality
HTS defects
Protection
Field Quality
Test issues
Windability
Notes: Mit for defects: 1: cut the weak portion of the cable and joint. 2: remove. 3: targeting shorter batches of 4 mm wide (or narrower) tape which have proven to be manufactured in a more controlled way.
Mit for prot: Anticipate a quench with an early detection. A further measure could be to pass from insulated to Controlled Resistance (CI) mode.
Mit for FQ: 1: in the design phase consider a narrow tape; 2: during testing, we will verify that the errors are stable ramp-to-ramp, such as to implement feed-forward correcting strategies.
Mit for win: more demanding specs or winding tension profile.
Mit for cryogenic: enhance cooling power or run a temporary test in Lhe or LN2

## Slide 24: Risks and costs summary
Main mitigations:
Field quality: in the design phase consider a narrow tape (4 mm, or less).
Protection: pass from insulated to Controlled Resistance (CI) mode.
Defects: cut the weak portion of the cable and optimize joint procedure.
Test issues: Increase the cooling power with a suitable additional variable temperature heat exchanger.
Windability: Ask for more demanding thickness specification to the manufacturerand act on the design of the flat coil geometry.
HTS defects
Field Quality
Protection
Test issues
Windability
Notes: Mit for defects: 1: cut the weak portion of the cable and joint. 2: remove. 3: targeting shorter batches of 4 mm wide (or narrower) tape which have proven to be manufactured in a more controlled way.
Mit for prot: Anticipate a quench with an early detection. A further measure could be to pass from insulated to Controlled Resistance (CI) mode.
Mit for FQ: 1: in the design phase consider a narrow tape; 2: during testing, we will verify that the errors are stable ramp-to-ramp, such as to implement feed-forward correcting strategies.
Mit for win: more demanding specs or winding tension profile.
Mit for cryogenic: enhance cooling power or run a temporary test in Lhe or LN2

## Slide 25: Risks and costs summary
Object | Year | Cost [€] | Cost + IVA [€]
3 km of HTS tape | 1+2 | 55 500 | 67 710
Coils mechanical components | 1 | 22 800 | 27 816
Curved mechanical supports | 2 | 12 250 | 14 945
Cryogenic test components | 2 | 25 300 | 30 866
Presentation at conferences | 1+2 | 3 600 | 3 600
Total | 1+2 | 119 450 | 144 937
Costs analysis considered:
Tape quotation was obtained addressing medium performance, commerically available 4 mm HTS tape
Mechanical components for each coil were based on a preliminary design for small HTS racetrack coil
Curved mechanical supports and cryogenic tests component are based on SIG mechanics and from the preparation of the test of a single ESMA coil

## Slide 26
Final recap and conclusions
Given the expertise gained from INFN-led project as SIG e HITRI+ on SC gantry, a classical CCT design was adapted to be realized in a modular structure:
  The goal is to realize a small-scale HTS dipole magnet demonstrator consisting of 10 modules for each layer.
The project sets the first milestone towards a next generation of ion gantries introducing:
  Energy saving.
  Industrial scalability.
  Compact gantries.

## Slide 27: The end

## Slide 28: Backup Slides

## Slide 29
Thickness Inhomogeneity
Supplier Spec 67 µm ± 10% (from 59 µm to 74 µm)
01/12/2025
Tapes may show thickness inhomogeneity commonly referred to as “dog-bone”, occurring during the electroplating of the final copper layer.
This may lead to:
Localized stresses
Winding issues

## Slide 30
Inclusion Characterisation
64 Spools fully de-spooled and inspected for defects
Minimum Inclusion thickness tracked: 30 µm
Inclusions: > 400
95% Inclusion on the good side (YBCO side)
80% Inclusion on the edge areas
Inclusion Genesis – Silver Sputtering
small silver particles can stick to the rollers in the tape transport system
they stick to the tape surface
they get coated with copper during electroplating
01/12/2025

## Slide 31: Characterization of HTS stacks
Mechanical measurement will be followed by electrical measurements to assess a possible tape degradation:
Variable uniaxial compressive load
Different stack conditions
01/12/2025

## Slide 32: Resources availability
Endorsement of the magnet group leader at LASA for the use of the following resources:
Group technicians for coil assembly and manufacturing up to 2 FTE
01/12/2025